ASSIGNMENT

Course Code         : CSE 2201

Course Title 		:  Software Engineering & System Analysis

Submission Date : 5th November, 2025

Assignment Title :

End-to-End Software Project Management Scheme for a Cross-Platform Student Productivity Mobile Application

Name          : ABDULLAH ATIF

Student ID  : 241311051

Section       : B

Semester    : 4th Semester

Batch         : 34th

Submitted By

Submitted To

Name       : Mohammad Faisal Al-Naser

Designation : Lecturer

Signature of Teacher

Varendra University

Department of Computer Science and Engineering

Project Title:

StudyBuddy – A Mobile Learning Assistant App

- 1. Project Initiation

- Goal: Design and develop a full-featured, cross-platform mobile app on iOS & Android using React Native that helps university students advance their productivity by centralizing study schedules, progress tracking, and peer collaboration.

- Key Features & Functionalities (In Scope):

- User Authentication: Secure, seamless sign-on via email/password, Google, and University SSO (Critical Path).

- Personal Dashboard: An intuitive, at-a-glance view of the user's critical path items-upcoming exams, assignments, scheduled study sessions.

- Smart Scheduler: An AI-supported study planner, using the Pomodoro Technique to optimize time management.

- Study Groups & Collaboration: Functionality to create/join groups, share curated notes, and real-time in-app chat integration.

- Progress Analytics: Visual, data-driven reports in the form of charts/graphs on cumulative study hours and performance metrics by subject.

- Resource Library: Securely upload, store, and share university resources such as PDFs, flashcards, and verified past papers.

- Push Notifications: Timely reminders of scheduled tasks, group activity, and upcoming deadlines to ensure maximum task completion.

- Out of Scope (Initial Release - MVP Focus):

- Native Windows/macOS Desktop Application

- Complex Offline-first data synchronization.

- Advanced AI-driven tutoring/content generation. Subject to a future phase, Phase II.

- Stakeholders and Roles:

| Stakeholder | Role |  | Key Responsibilities & Engagement |
| --- | --- | --- | --- |
| Project Sponsor |  | University Authority | High-level accountability for project funding, strategic alignment with university goals, and scope sign-off. |
| Project Manager | “X” (Student Lead) |  | End-to-end project oversight: Resource allocation, risk mitigation, schedule adherence, and all external reporting. |
| Development Team | 5 Student Developers |  | Core execution: Feature development, technical implementation, unit/integration testing, and deployment support. |
| UI/UX Designer | Team Member |  | User experience excellence: Wireframing, prototyping, user flow definition, and accessibility compliance. |
| End Users | University Students |  | Critical feedback loop: Alpha/Beta testing, validating user stories, and providing post-launch utilization data. |
| IT Admin | University IT Dept. |  | Technical gatekeeper: Providing API access for SSO integration and ensuring security/data compliance. |

- Project Charter:

- Project Title: StudyBuddy Mobile App

- Objective: The objective will be to deliver a user-centric, highly scalable mobile application that is proven to measurably improve student productivity and peer-to-peer collaboration by May 30, 2026.

- Constraints (The Triple Constraint + Team):

- Budget: 480,000 BDT - Comprehensive funding covering stipends to cloud infrastructure and quality assurance.

- Timeline: 6 months, from December 1, 2025, through May 30, 2026.

- Team: 5 highly motivated, part-time student developers (15 hours/week commitment).

- Technology: Cross-platform requirement using React Native.

- Assumptions:

- Prompt access to the necessary university SSO API documentation and sandboxes.

- The original cloud architecture at Firebase/AWS will scale to support up to 1000 users on standard/free tiers, before the requirement for major paid upgrades.

- Team members reliably devote the agreed-upon 15 hours/week to the project.

- Success Indication-Observation Criteria :

- User Adoption: Achieve a baseline of 500+ active, unique users within the first academic semester post-launch.

- Quality Score: Keep an average rating of 4.0+ in the stores on both platforms.

- Usability: Obtain a 90 percent completion rate for major features, such as scheduling a study session or creating a group.

- Project Delivery: On-time and strictly within the 480,000 BDT budget.

- 2. Project Planning

- Work Breakdown Structure (WBS):

The WBS defines all project work necessary to reach the objective, logically structured.

1.0 Project Initiation (PM Focus):

1.1 Scope Definition & Sign-off

1.2 Stakeholder Analysis & Communication Plan

1.3 Project Charter Formalization

2.0 Requirements & Design (UX/Design Focus):

2.1 Detailed User Stories & Acceptance Criteria

2.2 Wireframes & Prototypes Comprehensive UI/UX (Figma)

2.3 Robust Database Schema Design & Normalization

2.4 API Design & Technical Specification Documentation

3.0 Development: Coding & Integration Focus:

3.1 Backend/Cloud Infrastructure Setup & Configuration

3.2 Frontend, React Native - Core Component Library Development

3.3 Secure Authentication & SSO Module Implementation

3.4 Smart Scheduler & Notification Engine Development

3.5 Implementation of study groups, chat, and resource sharing

3.6 Progress Analytics Dashboard & Reporting Module

3.7 Security Audits (Input Validation, API Keys)

4.0 Testing & Quality Assurance (QA Focus):

4.1 Unit Testing (Code Level Coverage > 80%)

4.2 Integration Testing: API & Database Interoperability

4.3 User Acceptance Testing - UAT with target users (beta group)

4.4 Performance & Load Testing

5.0 Deployment & Closure (Final PM Phase):

5.1 App Store & Google Play Submission & Approval

5.2 Initial User Onboarding & Support Documentation

5.3 Comprehensive Project Report, Handoff, and Lessons Learned

- Project Schedule (Gantt Chart)

The schedule is based on a Scrum methodology but defines the macro-level phase durations.

| Task (WBS Link) | Duration | Start Date | End Date | Dependencies (Predecessor) |
| --- | --- | --- | --- | --- |
| 1.0 Project Initiation | 1 week | Dec 1 | Dec 7 | — |
| 2.0 Requirements & Design | 3 weeks | Dec 8 | Dec 28 | 1.0 |
| 3.1 Backend Setup | 2 weeks | Dec 29 | Jan 11 | 2.0 |
| 3.3 Authentication Module | 2 weeks | Jan 12 | Jan 25 | 3.1 (High Priority) |
| 3.2 Frontend Core Dev | 6 weeks | Jan 12 | Feb 22 | 2.0 (Parallel to Backend) |
| 3.4 Scheduler Engine | 3 weeks | Jan 26 | Feb 15 | 3.1 |
| 3.5 Study Groups | 3 weeks | Feb 16 | Mar 8 | 3.1 |
| 3.6 Analytics Dashboard | 2 weeks | Mar 9 | Mar 22 | 3.1 |
| 4.0 Testing (All Phases) | 4 weeks | Mar 23 | Apr 19 | 3.0 (Development Complete) |
| 5.1 Deployment | 2 weeks | Apr 20 | May 3 | 4.0 |
| 5.3 Closure & Report | 3 weeks | May 4 | May 30 | 5.1 |

Critical Path: 1.0 Initiation → 2.0 Design → 3.1 Backend Setup → 3.3/3.4 Development → 4.0 Testing → 5.1 Deployment. Testing is the longest post-development phase and a critical constraint.

- 2.3 Budget Allocation (Total: 480,000 BDT)

| Category | Item | Rationale | Cost (BDT) |
| --- | --- | --- | --- |
| Human Resources | Developer Stipends (5 × 6 months) | Competitive compensation (approx. 6,000 BDT/member/month) to ensure retention and high commitment. | 180,000 |
|  | Project Manager Stipend (6 months) | Higher stipend for leadership, risk, and administrative overhead (approx. 10,000 BDT/month). | 60,000 |
| Cloud & Tools | Firebase (Premium Auth/Storage/DB) | Scalable, pay-as-you-go hosting, crucial for high-traffic features like real-time chat. | 75,000 |
|  | AWS S3/Cloudflare (CDN/Storage) | Offload static content and files from Firebase to optimize costs and global delivery. | 20,000 |
|  | Figma Pro/JIRA/Confluence | Professional licenses for design collaboration and rigorous issue tracking/documentation. | 15,000 |
|  | App Store/Google Play Fees | Annual registration and console fees for submission compliance. | 10,000 |
| Quality Assurance (QA) | Test Devices (2 iOS/2 Android) | Purchase/lease of diverse test devices to ensure cross-device compatibility and minimize bugs. | 80,000 |
| Miscellaneous | Domain, SSL, Initial Marketing Campaign | Costs for a professional domain and a small, targeted digital launch campaign. | 40,000 |
| Contingency Reserve | 5% Buffer | Reserve for unforeseen technical issues or critical scope changes. | 10,000 |
| Total Project Budget |  |  | 480,000 BDT |

- 3. Team Formation

- Roles and Expert Responsibilities

The team utilizes the available resources by assigning clear, complementary roles.

| Role | Member | Expert Responsibilities |
| --- | --- | --- |
| Project Manager | “A” | Project control: Scheduling, financial tracking, external communication, and risk mitigation. |
| Lead Developer | “B” | Technical Authority: Defines architecture, code standards, manages CI/CD pipeline, and performs code reviews. |
| Frontend Developer | “C” | User Interface (UI) Execution: Implements all React Native components and state management. |
| Backend Developer | “D” | System Logic: Manages Firebase services, develops RESTful APIs, and ensures data security/integrity. |
| UI/UX Designer | “E” | Design Authority: User research, interactive prototyping, and delivering final design specifications. |
| QA Tester (Integrated) | “F” | Quality Control: Creates and executes test plans, manages bug tickets, and facilitates UAT. |

- Organizational Chart

The chart illustrates a flat, project-focused structure ensuring efficient communication channels directly to the Project Manager.

Project Sponsor (Authority)

↓

Project Manager (“X”)

↓

┌───────────────┴───────────────┐

↓                                           ↓                                            ↓

Lead Dev (“B”)                UI/UX (“E”)                           QA (“F”)

↓

Development Team (“C”, “D”)

- 4. Risk Management

- Risk Identification and Prioritization: We identify key risks across the project lifecycle and assess their potential impact.

| Risk ID | Risk Description | Category | Likelihood (L) | Impact (I) | Priority |
| --- | --- | --- | --- | --- | --- |
| R1 | SSO Integration Failure/Delays | Technical | Medium | High | High |
| R2 | Team Member Attrition | Resource | High | High | Critical |
| R3 | Scope Creep (Feature Requests) | Management | Medium | Medium | Medium |
| R4 | App Store Policy Rejection | Compliance | Low | High | High |
| R5 | Cloud Service Cost Overrun | Financial | Low | Medium | Low |

- Risk Probability-Impact Matrix: This visual tool focuses attention on high-priority risks (High Likelihood/High Impact).

High Impact (I)

↑

High      L    | R1 ● | R2 ●  |

|--------|--------|

Medium L   | R3 ●  |          |

|--------|--------|

Low       L   | R4 ●  | R5 ●  |

----------------→ High Likelihood (L)

Focus: R1 & R2 require immediate and proactive mitigation strategies.

- Risk Mitigation Plan: Proactive Response:

| Risk | Mitigation Strategy (Proactive) | Owner | Contingency (Reactive) |
| --- | --- | --- | --- |
| R1 | Initiate SSO API handshake/sandbox testing in Sprint 1 (Dec 1-14). | “B” | Develop a robust email/social auth fallback system and defer SSO integration to Phase II if necessary. |
| R2 | Mandate cross-training on key components and conduct weekly psychological safety check-ins. | “X” | Maintain an updated list of pre-vetted backup student developers for rapid recruitment and onboarding (funded by Contingency Reserve). |
| R3 | Establish a formal Change Control Board (CCB) that must approve any new requirement after Week 3. | “X” | De-prioritize the lowest-value existing feature to accommodate any approved change within the timeline. |
| R4 | Dedicated review of App Store Guidelines by “E” / “F” in the design phase. | “E” | Budget a 2-week buffer in the schedule to address and re-submit the app after rejection. |
| R5 | Set up real-time billing alerts on Firebase/AWS dashboards and review expenses weekly. | “X” | Pivot to the standard (lower-cost) Firebase database structure instead of specialized cloud functions if costs spike. |

- 5. Development Methodology

- Methodology: Agile (Scrum)

Justification for Choosing Agile (Scrum)

  - Customer-Centric: The project fundamentally relies on University students' (End User) feedback in order to confirm some features like Smart Scheduler and Study Groups. Scrum supports this with frequent Sprint Reviews.

  - Adaptability: With the part-time team and the very real likelihood that the initial requirements will evolve-as indeed may happen within a university IT-bound context-iterative and flexibility are imperative.

  - Early Value Delivery: Agile prioritizes giving an MVP out as quickly as possible to ensure we launch with core features, iterate, and capture maximum value within the 6-month constraint..

- Sprint Breakdown (6 x 2-week Sprints):

The project is structured into six focused, two-week sprints to maintain velocity and deliver continuous integration.

| Sprint | Dates | Goal | Key Deliverables & Focus |
| --- | --- | --- | --- |
| Sprint 1 | Dec 29 – Jan 11 | Foundation | Secure Login/Registration, Dashboard UI Skeleton, Initial Backend Setup. |
| Sprint 2 | Jan 12 – Jan 25 | Core Engine I | Smart Scheduler functionality, Push Notification service integration. |
| Sprint 3 | Jan 26 – Feb 8 | Collaboration | Study Group creation, Real-time chat basic implementation. |
| Sprint 4 | Feb 9 – Feb 22 | Resource & Data | Resource Library upload/view functionality, Basic Progress Analytics data collection. |
| Sprint 5 | Feb 23 – Mar 8 | Insights & Polish | Visual Analytics Reports, Final UI/UX review and bug backlog clearance. |
| Sprint 6 | Mar 9 – Mar 22 | Final QA/UAT | End-to-end testing, final security review, and User Acceptance Testing sign-off. |

Daily Standups: A daily quick sync, 15 minutes via Discord, covers 'What was done yesterday,' 'What will be done today,' and 'Blockers/Issues.'

Sprint Reviews: Formal presentation and demonstration of the working software, at the end of each sprint, with the Project Sponsor and a small group of end-users.

- 6. Conclusion

The StudyBuddy project is based on a very strong, professional management scheme. The deliberate choice of the Agile (Scrum) methodology, combined with a realistic budget of BDT 480,000 and a proactive risk mitigation plan, promises a high probability of success.

This strategic approach ensures:

- Measurable success is defined by clear KPIs: 500+ active users, 4.0+ ratings.

- Resource Optimization: Efficient use of the budget of 480,000 BDT by the 5-member team.

- High Quality: Through integrated QA by Riley and frequent user feedback loops.

This scheme meets not only the academic requirements but also functions as a deployable professional-grade template to deliver high-impact mobile products on time and within budget.